## Stats
Enhancements/Interfaces/Workflow/Forms/Conversions
Recommendation | (Multiple Items) | Recommendation | (Multiple Items) | Recommendation | (Multiple Items)
Row Labels | Count of Business Process | Row Labels | Count of Business Process | Row Labels | Count of RICEF Object
Conversion | 51 | H | 31 | Cash to Invest | 21
ABAP | 30 | L | 31 | Hire to Retire | 28
IMPORT | 8 | M | 109 | Offer to Cash | 59
LSMW | 11 | VH | 4 | Plan to Report | 38
MANUAL | 2 | Grand Total | 175 | Procure to Pay | 29
ENH/FRM | 94 |  |  | Grand Total | 175
ABAP | 5
ENH | 64
FRM | 17
WKF | 8
Interface | 27
INB | 14
OUT | 13
Report | 3
ABAP | 3
Grand Total | 175
Reports
Recommendation | (Multiple Items)
Row Labels | Count of RICEF Object
Cash to Invest | 9
Hire to Retire | 29
Offer to Cash | 11
Plan to Report | 13
Procure to Pay | 27
Grand Total | 89

## WICEF
Type | Business Process | RICEF Object | CR Number | Complexity | Name of RICEFW Object | RICEFW Type
Conversion | Cash to Invest | CTI-ERP-CNV-0021 |  | M | Securities Accounts Conversion for Outstanding Investments | ABAP
Conversion | Cash to Invest | CTI-ERP-CNV-0022 |  | M | Security Class (CUSIP Master Record) Conversion | LSMW
Conversion | Cash to Invest | CTI-ERP-CNV-0023 |  | M | Cash Balance Conversion | LSMW
Conversion | Cash to Invest | CTI-ERP-CNV-0024 |  | M | Investment Position Conversion | ABAP
Conversion | Cash to Invest | CTI-ERP-CNV-0032 |  | M | Bank Directory Conversion | ABAP
ENH/FRM | Cash to Invest | CTI-ERP-ENH-0052 |  | M | Improve Hit Rate for Bank/Trustee Reconciliation Enhancement | ENH
ENH/FRM | Cash to Invest | CTI-ERP-ENH-0053 |  | M | Badin - Profit Center as Account Assignment Object for Investments | ENH
ENH/FRM | Cash to Invest | CTI-ERP-ENH-0065 |  | M | Convert M&T Bank st. in TRANEXT format to BAI2 format | ENH
ENH/FRM | Cash to Invest | CTI-ERP-ENH-0093 |  | H | Investment Trading Grid | ENH
ENH/FRM | Cash to Invest | CTI-ERP-ENH-0094 |  | L | Bank statement pre-processor | ENH
ENH/FRM | Cash to Invest | CTI-ERP-ENH-0247 | CR_045 | L | Derive Fund and Profit Center for CTI / Banking | ENH
ENH/FRM | Plan to Report | CTI-ERP-ENH-0240 | CR_087 | M | ACH Payment Enhancements | ENH
ENH/FRM | Cash to Invest | CTI-ERP-FRM-0030 |  | M | Investment Form - Trustee - Purchase and Sell Letter | FRM
ENH/FRM | Cash to Invest | CTI-ERP-FRM-0040 |  | M | Covering Letter to Payment file - all banks | FRM
Interface | Cash to Invest | CTI-ERP-INB-0013 |  | L | Electronic Bank Statement Interface for Cash Transactions (BAI2 Format) - Wells Fargo Bank | INB
Interface | Cash to Invest | CTI-ERP-INB-0014 |  | M | Electronic Bank Statement Interface for Cash Transactions (Bank Custom Format) - M & T Bank | INB
Interface | Cash to Invest | CTI-ERP-INB-0015 |  | L | Electronic Bank Statement Interface for Cash Transactions (BAI2 Format) - BNY-Mellon Bank | INB
Interface | Cash to Invest | CTI-ERP-INB-0016 |  | L | Electronic Bank Statement Interface for Cash Transactions (BAI2 Format) - U.S. Bank | INB
Interface | Cash to Invest | CTI-ERP-INB-0017 |  | L | Electronic Bank Statement Interface for Cash Transactions (BAI2 Format) - Capital One Bank | INB
Interface | Cash to Invest | CTI-ERP-INB-0018 |  | L | Electronic Bank Statement Interface for Cash Transactions (BAI2 Format) - JPM Chase | INB
Interface | Cash to Invest | CTI-ERP-INB-0019 | CR_061 | L | Receivables Lockbox Inbound Interface | INB
Interface | Cash to Invest | CTI-ERP-INB-0036 |  | L | Electronic Bank Statement Interface for Cash Transactions (BAI2 Format) - Key Bank | INB
Interface | Cash to Invest | CTI-ERP-INB-0037 |  | M | Investment Purchases and Sales Upload from Invest System | INB
Conversion | Hire to Retire | HTR-ERP-CNV-0009 |  | H | Position Conversion | ABAP
Conversion | Hire to Retire | HTR-ERP-CNV-0010 |  | M | Employee Conversion | ABAP
Conversion | Hire to Retire | HTR-ERP-CNV-0033 |  | M | Employee Travel Privileges Conversion | ABAP
Conversion | Hire to Retire | HTR-ERP-CNV-0034 |  | M | Employee Communication Information Conversion | ABAP
Conversion | Hire to Retire | HTR-ERP-CNV-0035 |  | M | Position Cost Distribution Conversion | ABAP
Conversion | Hire to Retire | HTR-ERP-CNV-0036 |  | M | Employee Salary History Conversion | ABAP
Conversion | Hire to Retire | HTR-ERP-CNV-0037 |  | M | Organizational Units - Managers (Chiefs) | ABAP
Conversion | Hire to Retire | HTR-ERP-CNV-0038 |  | M | Organizational Units - Addresses | ABAP
ENH/FRM | Hire to Retire | HTR-ERP-ENH-0006 |  | H | Payroll Labor Distribution | ENH
ENH/FRM | Hire to Retire | HTR-ERP-ENH-0009 | CR_056 | H | Encumber Travel Request in Funds Management | ENH
ENH/FRM | Hire to Retire | HTR-ERP-ENH-0010 |  | M | GSA-Approved Lodging Rate Notification and Excess Rate Justification | ENH
ENH/FRM | Hire to Retire | HTR-ERP-ENH-0011 |  | H | Out-of-State Travel Notification and Designation (Including Justification Questions) | ENH
ENH/FRM | Hire to Retire | HTR-ERP-ENH-0012 |  | L | Post-Travel Expense Reimbursement Submittal Reminder | ENH
ENH/FRM | Hire to Retire | HTR-ERP-ENH-0015 |  | M | Payroll Results and Distribution Table | ENH
ENH/FRM | Hire to Retire | HTR-ERP-ENH-0066 |  | L | Custom Employee Info type | ENH
ENH/FRM | Hire to Retire | HTR-ERP-ENH-0067 |  |  | Custom BW Extractor to Support Employee Reporting | ENH
ENH/FRM | Hire to Retire | HTR-ERP-ENH-0068 |  | M | Employee Compensation Adjustment Program | ENH
ENH/FRM | Hire to Retire | HTR-ERP-ENH-0069 |  | L | Default values for info type | ENH
ENH/FRM | Hire to Retire | HTR-ERP-ENH-0070 |  | M | Determine General Ledger Account Using Trip Activity Type | ENH
ENH/FRM | Hire to Retire | HTR-ERP-ENH-0071 |  | L | Suppress Unused Attributes for Organization and Staffing (transaction PPOSE) | ENH
ENH/FRM | Hire to Retire | HTR-ERP-ENH-0072 |  | L | Suppress Create Attachment Option for Generic Object Services (GOS) | ENH
ENH/FRM | Hire to Retire | HTR-ERP-ENH-0074 | CR_015 | L | IT0009 enhancement to clear company code | ENH
ENH/FRM | Hire to Retire | HTR-ERP-ENH-0238 | CR_072 | L | Custom Table to Support BI | ENH
ENH/FRM | Hire to Retire | HTR-ERP-FRM-0243 | CR_103 | M | Travel reimbursement warrant form | FRM
Interface | Hire to Retire | HTR-ERP-INB-0004 |  | M | ADP to SAP Payroll Interface | INB
ENH/FRM | Hire to Retire | HTR-ERP-WKF-0002 |  | H | Travel Request Workflow | WKF
ENH/FRM | Hire to Retire | HTR-ERP-WKF-0003 |  | H | Employee Expense Reimbursement Workflow | WKF
Conversion | Hire to Retire | HTR-MAN-CNV-0001 |  | M | Enterprise Organization | MANUAL
ENH/FRM | Offer to Cash | OTCD-BI-ENH-0026 |  |  | Custom BW Extractor to Support Debt Management Reporting | ENH
Conversion | Offer to Cash | OTCD-ERP-CNV-0013 |  | H | Outstanding Bonded Debt Master Data Conversion | ABAP
Conversion | Offer to Cash | OTCD-ERP-CNV-0014 |  | H | Securities Accounts Conversion for Outstanding Bonded Debt | ABAP
Conversion | Offer to Cash | OTCD-ERP-CNV-0020 |  | M | Import house bank accounts | ABAP
Conversion | Offer to Cash | OTCD-ERP-CNV-0030 |  | M | Bonded Debt Position (Trades) Conversion | ABAP
Conversion | Offer to Cash | OTCD-ERP-CNV-0051 |  | M | Internal Order Conversion | LSMW
Conversion | Offer to Cash | OTCD-ERP-CNV-0052 |  | M | Fund Conversion | LSMW
Conversion | Offer to Cash | OTCD-ERP-CNV-0053 |  | M | Business Partner Conversion for Bonded Debt & Investment | ABAP
Conversion | Offer to Cash | OTCD-ERP-CNV-0061 |  | H | Change Class Data (conditions) for Debt | ABAP
ENH/FRM | Offer to Cash | OTCD-ERP-ENH-0018 |  | M | Security Class Custom Fields for Bonded Debt | ENH
ENH/FRM | Offer to Cash | OTCD-ERP-ENH-0019 |  | M | Enter Original Redemption Schedule for Bonded Debt Redeemed (Transaction Z_FWBS) | ENH
ENH/FRM | Offer to Cash | OTCD-ERP-ENH-0020 |  | M | Update Payment Schedule for Bonded Debt Redeemed (Transaction Z_FWZZ) | ENH
ENH/FRM | Offer to Cash | OTCD-ERP-ENH-0021 |  | M | Account Codes for Posting of Bonded Debt | ENH
ENH/FRM | Offer to Cash | OTCD-ERP-ENH-0022 | CR_141 | M | Reclassify Long-Term to Short-Term Bonded Debt Payable | ENH
ENH/FRM | Offer to Cash | OTCD-ERP-FRM-0010 |  | H | Bonded Debt Form - Debt Service - Funds Transfer Letter to Bank | FRM
ENH/FRM | Offer to Cash | OTCD-ERP-FRM-0011 |  | H | Bonded Debt Form - Redemption - Trustee Letter | FRM
ENH/FRM | Offer to Cash | OTCD-ERP-FRM-0012 |  | M | Bonded Debt Form - Debt Service - Daily & Weekly Variable Rate - No Bonds Proceeds Report | FRM
ENH/FRM | Offer to Cash | OTCD-ERP-FRM-0031 |  | L | Loan Statement | FRM
ENH/FRM | Offer to Cash | OTCD-ERP-FRM-0032 |  | L | Customer Account statement | FRM
ENH/FRM | Offer to Cash | OTCD-ERP-FRM-0038 |  |  | Bank Transfer Order | FRM
ENH/FRM | Offer to Cash | OTCD-ERP-FRM-0039 |  |  | Escrow Account Statement | FRM
Interface | Offer to Cash | OTCD-ERP-INB-0023 |  | L | ProLink to SAP - Disbursement Requisition Interface | INB
Interface | Offer to Cash | OTCD-ERP-INB-0026 |  | M | ProLink to SAP - Participating Loan Payment Interface | INB
Interface | Offer to Cash | OTCD-ERP-INB-0027 |  | M | ProLink to SAP - Loan Fee Interface | INB
Interface | Offer to Cash | OTCD-ERP-INB-0034 |  | M | ProLink to SAP - Loan Escrow Disbursement Request Interface | INB
Interface | Offer to Cash | OTCD-ERP-OUT-0003 | CR_060 | M | SAP to ProLink - Month-End Outstanding Bonded Debt Payables | OUT
Interface | Offer to Cash | OTCD-ERP-OUT-0004 | CR_060 | M | SAP to ProLink - Month-End Bank Account Balances | OUT
Interface | Offer to Cash | OTCD-ERP-OUT-0014 | CR_060 | M | SAP to ProLink - Bond Class Master Data Interface | OUT
Interface | Offer to Cash | OTCD-ERP-OUT-0016 | CR_060 | M | SAP to ProLink - Bond Redemption Interface | OUT
Interface | Offer to Cash | OTCD-ERP-OUT-0017 | CR_061 | M | SAP to ProLink - Credit enhancement Interface | OUT
Interface | Offer to Cash | OTCD-ERP-OUT-0022 | CR_020 | L | Encrypted Payment File Interface - US Bank | OUT
Interface | Offer to Cash | OTCD-ERP-OUT-0023 | CR_020 | M | Encrypted Payment File Interface - Wells Fargo | OUT
Interface | Offer to Cash | OTCD-ERP-OUT-0024 | CR_062 | M | Encrypted Payment File Interface - Capital One | OUT
Interface | Offer to Cash | OTCD-ERP-OUT-0025 | CR_020 | M | Encrypted Payment File Interface - BNY Mellon | OUT
Interface | Offer to Cash | OTCD-ERP-OUT-0026 |  | M | Encrypted Payment File Interface - JPM Chase | OUT
Interface | Offer to Cash | OTCD-ERP-OUT-0027 | CR_020 | M | Non-Standard Payment File Interface - M&T Bank | OUT
Interface | Offer to Cash | OTCD-ERP-OUT-0028 |  | H | Encrypted Payment File Interface - Key Bank | OUT
Conversion | Offer to Cash | OTCD-MAN-CNV-0003 |  | M | Internal Order Groups | IMPORT
Interface | Offer to Cash | OTCD-New |  | M | ProLink to SAP - Bonds Issuance initiation | INB
Conversion | Offer to Cash | OTCL-ERP-CNV-0025 | 73 | H | Loan and Billing Business Partner Conversion | LSMW
Conversion | Offer to Cash | OTCL-ERP-CNV-0026 | 74 | M | Loan Contract Conversion | ABAP
ENH/FRM | Offer to Cash | OTCL-ERP-ENH-0013 |  | H | Loan Bank Transfer Processing | ENH
ENH/FRM | Offer to Cash | OTCL-ERP-ENH-0054 |  | M | Extend Loan Contract Master Table for Profit Center, Internal Order and Fund Fields | ENH
ENH/FRM | Offer to Cash | OTCL-ERP-ENH-0055 |  | H | Extend Loan Account Assignments - Profit Center, Internal Order, Fund Fields | ENH
ENH/FRM | Offer to Cash | OTCL-ERP-ENH-0055 | CR_073 | H | Extend Loan Account Assignments - Profit Center, Internal Order, Fund Fields | ENH
ENH/FRM | Offer to Cash | OTCL-ERP-ENH-0249 | CR_045 | M | New Enhancement OTCL | ENH
ENH/FRM | Offer to Cash | PTR-ERP-ENH-0248 | CR_045 | L | Fringe Calculations | ENH
ENH/FRM | Procure to Pay | PTP-ERP-ENH-0256 | CR_150 | L | Catalog Transfer BADI for UNSPSC code to Material Group mapping | ENH
ENH/FRM | Offer to Cash | OTCL-ERP-ENH-0080 | CR_139 | H | New Calculation Basis- Create two more calculation basis | ENH
ENH/FRM | Procure to Pay | PTP-SRM-ENH-0037 | CR_129 | M | Vendor Replication – Updates to Minority Indicators | ENH
ENH/FRM | Hire to Retire | HTR-ERP-ENH-0253 | CR_128 | H | Travel Cost Allocation CR | ENH
ENH/FRM | Offer to Cash | OTCD-ERP-ENH-0252 | CR_122 | M | Lockbox processing and clearing logic enhancement | ENH
ENH/FRM | Offer to Cash | OTCD-ERP-ENH-0022 | CR_141 | H | LT to ST re-class of Debt – 1 Development Object and other Functional tasks | ENH
ENH/FRM | Offer to Cash | OTCL-ERP-FRM-0034 | CR_165 | M | Outgoing payments | ENH
ENH/FRM | Hire to Retire | HTR-ERP-ENH-0072 | CR_159 | L | Deactivating GOS for PR05 (Remove From Scope) | ENH
ENH/FRM | Offer to Cash | OTCD-ERP-ENH-0251 | CR_121 | M | Validate no partial payments / overpayments / on-account payments happen on HFA customer accounts | ENH
ENH/FRM | Offer to Cash | PTR-ERP-ENH-0250 | CR_045 | L | Substitution for CO Distribution | ENH
ENH/FRM | Offer to Cash | OTCL-ERP-ENH-0059 |  | H | Extend Online Payment Request Account Assignments - Profit Center, Internal Order, Fund Fields | ENH
ENH/FRM | Offer to Cash | OTCL-ERP-ENH-0062 |  | H | Enhanced Process for Inter-Bank Account Transfer Order Interface - Redistribute Payments Received to Bank Accounts | ENH
ENH/FRM | Offer to Cash | OTCL-ERP-ENH-0080 |  | M | NYSHCR - New Calculation Base | ENH
ENH/FRM | Offer to Cash | OTCL-ERP-ENH-0081 |  | M | Facility Field | ENH
ENH/FRM | Offer to Cash | OTCL-ERP-ENH-0082 |  | H | SAP Disburse multi-payments | ENH
ENH/FRM | Offer to Cash | OTCL-ERP-ENH-0082 | CR_054 | H | SAP Disburse multi-payments | ENH
ENH/FRM | Offer to Cash | OTCL-ERP-ENH-0083 |  | VH | Variable interest Bond and Loan creation | ENH
ENH/FRM | Offer to Cash | OTCL-ERP-ENH-0083 | CR_096 | VH | Variable interest Bond and Loan creation | ENH
ENH/FRM | Offer to Cash | OTCL-ERP-ENH-0083 | CR_073 | VH | Variable interest Bond and Loan creation | ENH
ENH/FRM | Offer to Cash | OTCL-ERP-ENH-0091 | CR_004 | L | new enhancement for fee calculation | ENH
ENH/FRM | Offer to Cash | OTCL-ERP-ENH-0095 |  | M | CMS to TRM (Debts information) | ENH
ENH/FRM | Offer to Cash | OTCL-ERP-ENH-0096 |  | M | CMS calculation for LOC amount | ENH
ENH/FRM | Offer to Cash | OTCL-ERP-ENH-0097 |  | M | CMS ENH to pull the project number | ENH
ENH/FRM | Plan to Report | OTCl-ERP-ENH-0246 | CR_095 | L | Alternate Payer | ENH
ENH/FRM | Offer to Cash | OTCL-ERP-FRM-0034 | CR_073 | M | Customer Invoice | FRM
ENH/FRM | Offer to Cash | OTCL-ERP-FRM-0045 |  | M | Billing form - Disburse | FRM
ENH/FRM | Offer to Cash | OTCL-ERP-FRM-0090 | CR_012 | H | New enhancement for Disbursement | FRM
Interface | Offer to Cash | OTCL-ERP-INB-0002 |  | M | ProLink to SAP - External Project Interface - Profit center & Internal Order | INB
Interface | Offer to Cash | OTCL-ERP-INB-0003 |  | M | ProLink to SAP - Bond Issue Fund Creation | INB
Interface | Offer to Cash | OTCL-ERP-INB-0020 |  | H | ProLink to SAP - Business Partner Interface (Loans) | INB
Interface | Offer to Cash | OTCL-ERP-INB-0022 | CR_057 | H | ProLink to SAP - Loan Contract Interface | INB
Interface | Offer to Cash | OTCL-ERP-INB-0030 | CR_065 | H | ProLink to SAP - Tax Credit Monitoring Fee Interface | INB
Interface | Offer to Cash | OTCL-ERP-INB-0031 | CR_166 | H | ProLink to SAP - Bond Issuance Cost Billing Interface | INB
Interface | Offer to Cash | OTCL-ERP-INB-0032 | CR_182 | H | ProLink to SAP - Grant Disbursement Request Interface | INB
Interface | Offer to Cash | OTCL-ERP-INB-0038 |  | M | Receivables Lockbox Inbound Interface - Mortgage Insurance Fund | INB
Interface | Offer to Cash | OTCL-ERP-INB-0045 | CR_003 | M | Prolink to SAP - BP Change | INB
Interface | Offer to Cash | OTCL-ERP-INB-0046 | CR_065 | H | Prolink to SAP - Create new Escrows | INB
Interface | Offer to Cash | OTCL-ERP-OUT-0007 | CR_052 | H | SAP to Prolink - Month-End Loan Activity and Balances Interface | OUT
Interface | Offer to Cash | OTCL-ERP-OUT-0010 | CR_006 | H | SAP to ProLink - Loan numbers will not be automatically synchronized with SAP loan contracts. | OUT
Interface | Offer to Cash | OTCL-ERP-OUT-0013 | CR_065 | H | SAP to ProLink - Tax Credit Monitoring Fee Document Number Interface | OUT
Interface | Offer to Cash | OTCL-ERP-OUT-0040 | CR_065 | M | Send the documents number created to IMS or ProLink | OUT
Interface | Offer to Cash | OTCL-ERP-OUT-0041 | CR_051 | M | SAP to Prolink - Disburse confirmation | OUT
Interface | Offer to Cash | OTCL-ERP-OUT-0042 |  | M | SAP to Prolink - Information from CMS | OUT
Interface | Offer to Cash | OTCL-ERP-OUT-0043 | CR_065 | H | IMS - Create new Escrows – Outbound | OUT
ENH/FRM | Offer to Cash | OTCL-ERP-WKF-0098 | CR_115 | H | SAP Disburse multi-payments | WKF
ENH/FRM | Procure to Pay | PTP-BI-ENH-0044 |  |  | Custom BW Extractor to Support Procurement Reporting | ENH
Conversion | Procure to Pay | PTP-ERP-CNV-0016 |  | M | Vendor Conversion - Business Partner | ABAP
Conversion | Procure to Pay | PTP-ERP-CNV-0058 |  | L | Materials- Basic, Purchasing, Accounting | LSMW
ENH/FRM | Procure to Pay | PTP-ERP-ENH-0092 | CR_0XX | L | Sourcing BADI | ENH
ENH/FRM | Procure to Pay | PTP-ERP-FRM-0018 |  | M | Vendor Payments Warrant Form - New York State - Tax and Finance | FRM
ENH/FRM | Plan to Report | PTR-ERP-FRM-0235 |  | M | Dental for Retiree Tracking Report | FRM
Interface | Procure to Pay | PTP-ERP-OUT-0002 | CR_082 | M | New York State - Tax and Finance - Vendor Payments Requested Interface | OUT
Interface | Procure to Pay | PTP-ERP-OUT-0020 | CR_082 | M | SAP to ProLink - Payment Interface | OUT
Interface | Procure to Pay | PTP-ERP-OUT-0020 | CR_170 | M | SAP to ProLink - Payment Interface | OUT
Interface | Procure to Pay | PTP-ERP-OUT-0021 |  | M | SAP to ProLink - Trade Vendor Interface | OUT
ENH/FRM | Procure to Pay | PTP-ERP-WKF-0009 |  | M | Vendor Invoice Workflow - Direct Pay | WKF
ENH/FRM | Procure to Pay | PTP-ERP-WKF-0015 | CR_005 | M | PO Invoices | WKF
ENH/FRM | Procure to Pay | PTP-ERP-WKF-0016 | CR_013 | M | Contract Approval | WKF
ENH/FRM | Procure to Pay | PTP-ERP-WKF-0017 | CR_078 | VH | Workflow to approve HCR warrants | WKF
Interface | Procure to Pay | PTP-New |  | M | Contract to MDM | OUT
Conversion | Procure to Pay | PTP-SRM-CNV-0018 | 80 | M | Open Contract Conversion | ABAP
Conversion | Procure to Pay | PTP-SRM-CNV-0019 | 79 | M | Open Purchase Order Conversion | ABAP
ENH/FRM | Procure to Pay | PTP-SRM-ENH-0036 |  | L | Vendor Diversity Indicator - Sourcing Lists | ENH
ENH/FRM | Procure to Pay | PTP-SRM-ENH-0037 | CR_090 | M | Enhance ECC to SRM Vendor Replication | ENH
ENH/FRM | Procure to Pay | PTP-SRM-ENH-0039 | CR_169 | M | Special Procurement Indicator - Purchase Orders | ENH
ENH/FRM | Procure to Pay | PTP-SRM-ENH-0039 | CR_169 | M | Special Procurement Indicator - Purchase Orders | ENH
ENH/FRM | Procure to Pay | PTP-SRM-ENH-0040 | CR_189 | M | Special Procurement Follow-On Document Tracking - From Shopping Carts | ENH
ENH/FRM | Procure to Pay | PTP-SRM-ENH-0041 | CR_169 | L | Special Procurement Indicator - Contracts | ENH
ENH/FRM | Procure to Pay | PTP-SRM-ENH-0041 | CR_169 | L | Special Procurement Indicator - Contracts | ENH
ENH/FRM | Procure to Pay | PTP-SRM-ENH-0050 |  | L | Prevent Creation of Ship-To Addresses | ENH
ENH/FRM | Procure to Pay | PTP-SRM-ENH-0236 | CR_058 | M | Implementation of Closeout BADI | ENH
ENH/FRM | Procure to Pay | PTP-SRM-FRM-0019 | CR_194 | L | Purchase Order Form | FRM
ENH/FRM | Procure to Pay | PTP-SRM-FRM-0020 |  | M | Solicitation Response Form - This object is on hold until vetted via Change Board. Interactive form being changed to static form. Need Adobe licensing to run interactive form. | FRM
ENH/FRM | Procure to Pay | PTP-SRM-FRM-0022 |  | L | Contract Form | FRM
ENH/FRM | Procure to Pay | PTP-SRM-FRM-0023 |  | L | Purchase Order Notification Form - Vendor | FRM
ENH/FRM | Procure to Pay | PTP-SRM-FRM-0024 |  | L | Contract Notification Form - Vendor | FRM
Interface | Procure to Pay | PTP-SRM-OUT-0018 |  | M | SAP to ProLink - Contract Interface | OUT
Interface | Procure to Pay | PTP-SRM-OUT-0019 |  | M |  | OUT
Interface | Procure to Pay | PTP-SRM-OUT-0018 | CR_170 | M | SAP to ProLink - Contract Interface | OUT
Interface | Procure to Pay | PTP-SRM-OUT-0019 | CR_170 | M |  | OUT
ENH/FRM | Procure to Pay | PTP-SRM-WKF-0004 |  | M | Shopping Cart Workflow (including special procurements) | WKF
ENH/FRM | Procure to Pay | PTP-SRM-WKF-0005 |  | M | Purchase Order Workflow | WKF
Conversion | Plan to Report | PTR-ERP-CNV-0001 |  | M | Financial Balances Conversion - Fiscal Year Ending October 31 | ABAP
Conversion | Plan to Report | PTR-ERP-CNV-0002 |  | M | Mid-Year Financial Balances Conversion - Fiscal Year Ending March 31 - AHC | ABAP
Conversion | Plan to Report | PTR-ERP-CNV-0008 |  | M | 2017/2018 Budget Conversion | ABAP
Conversion | Plan to Report | PTR-ERP-CNV-0028 |  | M | Customer Open Items | ABAP
Conversion | Plan to Report | PTR-ERP-CNV-0031 |  | M | Vendor Open Items | ABAP
Conversion | Offer to Cash | PTR-ERP-CNV-0050 |  | M | Profit Center Conversion | LSMW
Conversion | Plan to Report | PTR-ERP-CNV-0054 |  | M | General Ledger Account Conversion | LSMW
Conversion | Plan to Report | PTR-ERP-CNV-0055 |  | M | Funded Program Conversion | LSMW
Conversion | Plan to Report | PTR-ERP-CNV-0056 |  | M | Functional Area Conversion | LSMW
Conversion | Plan to Report | PTR-ERP-CNV-0057 |  | M | Commitment Item Conversion | LSMW
Conversion | Plan to Report | PTR-ERP-CNV-0059 |  | M | Cost Center Conversion | LSMW
Conversion | Plan to Report | PTR-ERP-CNV-0060 |  | M | Funds Center Conversion | LSMW
ENH/FRM | Plan to Report | PTR-ERP-ENH-0001 |  | H | General Ledger Adjustment Excel Upload | ENH
ENH/FRM | Plan to Report | PTR-ERP-ENH-0002 |  | L | Legacy to SAP Mapping Table - Programs and Accounts | ENH
ENH/FRM | Plan to Report | PTR-ERP-ENH-0003 |  | L | Legacy to SAP Mapping Table - Agencies, Programs, Centers and Units | ENH
ENH/FRM | Plan to Report | PTR-ERP-ENH-0007 |  | M | Budget Entry Excel Upload | ENH
ENH/FRM | Plan to Report | PTR-ERP-ENH-0239 | CR_085 | M | Two Enhancement for Lockbox User Exits | ENH
ENH/FRM | Plan to Report | PTR-ERP-ENH-0239 | CR_045 | M | Two Enhancement for Lockbox User Exits | ENH
ENH/FRM | Plan to Report | PTR-ERP-ENH-0245 | CR_110 | L | Prompt Pay Report Custom Tables | ENH
ENH/FRM | Offer to Cash | PTR-ERP-FRM-0046 |  | H | Dental Claim Form | FRM
ENH/FRM | Plan to Report | PTR-ERP-FRM-0224 | CR_112 | M | Wire Warrant | FRM
Interface | Plan to Report | PTR-ERP-INB-0001 | CR_179 | M | Emphasys Interface | INB
Interface | Plan to Report | PTR-ERP-OUT-0011 |  | M | ADP Interface | OUT
ENH/FRM | Plan to Report | PTR-ERP-WKF-0001 |  | M | Budget Entry Approval Workflow | WKF
Conversion | Offer to Cash | PTR-MAN-CNV-0002 |  | M | Profit Center Groups | IMPORT
Conversion | Plan to Report | PTR-MAN-CNV-0004 |  | M | Funds Center Groups | IMPORT
Conversion | Plan to Report | PTR-MAN-CNV-0005 |  | M | Funded Program Groups | IMPORT
Conversion | Plan to Report | PTR-MAN-CNV-0006 |  | M | Functional Area Groups | IMPORT
Conversion | Plan to Report | PTR-MAN-CNV-0007 |  | M | Commitment Item Groups | IMPORT
Conversion | Plan to Report | PTR-MAN-CNV-0008 |  | M | Budget Period Groups | IMPORT
Conversion | Plan to Report | PTR-MAN-CNV-0009 |  | M | Budget Period Conversion | MANUAL
Conversion | Plan to Report | PTR-MAN-CNV-0010 |  | M | Fund Groups | IMPORT
Conversion | Plan to Report | PTR-ERP-CNV-0031 | CR_148 | M | AP open item migration | ABAP
Conversion | Plan to Report | PTP-SRM-CNV-0018 | CR_158 | M | Life to Date Value in Open Contracts | ABAP
Conversion | Offer to Cash | OTCL-ERP-CNV-0254 | CR_131 | M | Bond Issuance Migration (Automated) | ABAP
Conversion | Hire to Retire | HTR-ERP-CNV-0257 | CR_155 | M | Employee History Comment Details | ABAP
Conversion | Plan to Report | PTP-ERP-CNV-0016 | CR_129 | M | Vendor Master | ABAP
ENH/FRM | Hire to Retire | HTR-BI-RPT-0211 | CR_175 | M | BI Report | ABAP
ENH/FRM | Plan to Report | PTR-ERP-ENH-0260 | CR_176 | L | Add logic to combinations of fund and profit center to error proof journal entries and for cash account range | ABAP
ENH/FRM | Offer to Cash | OTCL-ERP-RPT-0258 | CR_160 | M | Consolidated Loans Information for Bond Structuring | ABAP
ENH/FRM | Plan to Report | PTR-ERP-FRM-0259 | CR_164 | M | Tax and Insurance Escrow Accounts Form | FRM
ENH/FRM | Plan to Report | PTR-ERP-ENH-0261 | CR_184 | H | Vendor Split Invoice Entry Screen (Vendor Invoice 50/50 Split) | ABAP
ENH/FRM | Procure to Pay | PTP-ERP-FRM-0262 | CR_194 | H | Purchase Order Form (Output) Modifications | FRM
Interface | Plan to Report | PTR-ERP-OUT-0241 | CR_136 CR_182 | H | SAP Check Number for Grants Disbursement | OUT
ENH/FRM | Cash to Invest | CTI-ERP-ENH-0242 | CR_107 | H | Dealer/Broker Selection Application | ABAP
ENH/FRM | Cash to Invest | CTI-ERP-ENH-0255 | CR_141 | H | Long term to short term reclass of debt | ABAP
Report | Cash to Invest | CTI-ERP-RPT-0229 | CR_36 | M | Dealer Log Report | ABAP
Report | Offer to Cash | OTCL-ERP-RPT-0263 | CR_208 | L | Loan integrated cashflow | ABAP
Report | Offer to Cash | OTCL-ERP-RPT-0264 | CR_208 | L | Loan cashflow + Bond cashflow | ABAP

## Oldreports (hidden)
In Consultant's Plan (Travis) | Schedule Grouping | ID | Business Process | Function | RICEF Object | Functional Consultant | Complexity | Name of RICEFW Object | RICEFW Type | FS Due Date | FS Status | S4/SRM Dev Status | S4 Developer | BW Dev Status | BW Developer | BO Dev Status | BI Developer | All Dev Complete | in Scope | Planned Start Date | Planned End Date | Actual Start Date | Actual end Date | FUT Status | Planned Effort | Actual Effort | Efficiency Gain | NYS Resource (Primary/Secondary) | Comments
N |  | ID005 | Plan to Report | Budgeting | BI-ENH-0008 |  | M | Custom BW Cubes to Support Organizational Structure Reporting | EHN
N |  | ID001 | Hire to Retire, Procure to Pay, Plan to Report | Labor Distribution, Accounts Payable, Accounting,Costing | BI-ENH-0016 |  | L | Custom BW Cubes to Support Procurement Reporting | EHN
N |  | ID002 | Hire to Retire, Procure to Pay, Plan to Report | Labor Distribution, Accounts Payable, Accounting,Costing | BI-ENH-0017 |  | L | Custom BW Extractor to Support Procurement Reporting | EHN
N |  | ID004 | Offer to Cash | Debt Management | BI-ENH-0025 |  | M | SAP will not provide reporting of bonded debt information that will include all account assignment fields. | EHN
N |  | ID003 | Offer to Cash | Debt Management | BI-ENH-0026 |  | L | Custom BW Cubes to Support Budget Development | EHN
N |  | ID006 | Procure to Pay | Procurement | BI-ENH-0043 |  | L | Custom BW Cubes to Support Vendor Reporting | EHN
N |  | ID007 | Procure to Pay | Procurement | BI-ENH-0044 |  | L | Custom BW Extractor to Support Vendor Reporting | EHN
N |  | ID008 | Procure to Pay | Procurement | BI-ENH-0046 |  | L | Custom BW Cubes to Support Debt Management Reporting | EHN
Y | DBT1 | ID114 | Offer to Cash | Debt Management | ERP-RPT-0026 | Mary Loughran | VL | Credit Enhancement | RPT | 2018-09-27 | waiting revision |  |  | 100% | Selvaraj Mani | 100% | Tim Wilson | Yes |  | 2019-02-12 | 2019-02-12 |  | 2018-11-30
Y | SRM1 | ID165 | Procure to Pay | SRM – Purchase Order (Procure to Pay) | BI-RPT-0036 | Paul Hanifan | VL | Flexible Procurement | RPT |  | Approved | 100% | Kamaljit Singh | 100% | Selvaraj Mani | 100% | Tim Wilson | Yes |  | 2019-01-09 | 2019-01-09 | 2018-08-11 | 2018-09-05
Y | SRM1 | ID166 | Procure to Pay | SRM – Shopping Cart | BI-RPT-0083 | Paul Hanifan | VL | Approval Times | RPT |  | Approved |  |  | 100% | Selvaraj Mani | 100% | Tim Wilson | Yes |  | 2018-07-30 | 2018-09-11 | 2018-08-11 | 2018-09-05
Y | SRM1 | ID167 | Procure to Pay | SRM – Shopping Cart | BI-RPT-0084 | Paul Hanifan | VL | Ordered Shopping Carts per Requester | RPT | 2018-11-30 | Approved |  |  | 100% | Selvaraj Mani | 100% | Tim Wilson | Yes |  | 2018-07-30 | 2018-09-10 | 2018-08-11 | 2018-09-10
Y | SRM1 | ID168 | Procure to Pay | SRM – Shopping Cart | BI-RPT-0085 | Paul Hanifan | VL | Shopping Carts per Order | RPT | 2018-12-05 | Approved |  |  | 100% | Selvaraj Mani | 100% | Tim Wilson | Yes |  | 2018-07-30 | 2018-09-10 | 2018-08-11 | 2018-09-10
Y | SRM1 | ID169 | Procure to Pay | SRM – Shopping Cart | BI-RPT-0086 | Paul Hanifan | VL | Shopping Carts per Account Assignment | RPT | 2018-12-07 | Approved |  |  | 100% | Selvaraj Mani | 100% | Tim Wilson | Yes |  | 2018-07-30 | 2018-09-10 | 2018-08-11 | 2018-09-10
N | SRM2 | ID208 | Procure to Pay | Procurement | BI-RPT-0035 | Paul Hanifan |  | Flexible Organizational Structure Report | RPT |  | NA | NA |  | NA |  | NA |  | NA | n | 2018-07-30 | 2018-09-05 | [7 empty] | This is an ABAP Report. Removed from Scope. CR_007
Y | SRM1 | ID170 | Procure to Pay | SRM – Shopping Cart | BI-RPT-0087 | Paul Hanifan | VL | Shopping Carts per Product Category | RPT | 2018-12-12 | Approved |  |  | 100% | Selvaraj Mani | 100% | Tim Wilson | Yes |  | 2018-07-30 | 2018-09-11 | 2018-08-11 | 2018-09-10
Y | SRM1 | ID171 | Procure to Pay | SRM – Shopping Cart | BI-RPT-0088 | Paul Hanifan | VL | Shopping Carts per Vendor & Catalog | RPT | 2018-11-14 | Approved |  |  | 100% | Selvaraj Mani | 100% | Tim Wilson | Yes |  | 2018-07-30 | 2018-09-12 | 2018-08-11 | 2018-09-10
Y | SRM1 | ID172 | Procure to Pay | SRM – Shopping Cart | BI-RPT-0089 | Paul Hanifan | VL | Status of Shopping Carts | RPT | 2018-11-16 | Approved |  |  | 100% | Selvaraj Mani | 100% | Tim Wilson | Yes |  | 2018-07-30 | 2018-09-12 | 2018-08-11 | 2018-09-10
Y | SRM1 | ID173 | Procure to Pay | SRM – Contract | BI-RPT-0090 | Paul Hanifan | H | Contract Cockpit Spend | RPT |  | Approved |  |  | 100% | Selvaraj Mani | 100% | Tim Wilson | Yes |  | 2018-07-30 | 2018-09-12 | 2018-08-11 | 2018-09-10
Y | SRM1 | ID174 | Procure to Pay | SRM – Contract | BI-RPT-0091 | Paul Hanifan | VL | Contract Alerts | RPT |  | Approved |  |  | 100% | Selvaraj Mani | 100% | Tim Wilson | Yes |  | 2018-07-30 | 2018-09-05 | 2018-08-11 | 2018-09-10
Y | SRM1 | ID175 | Procure to Pay | SRM – Contract | BI-RPT-0092 | Paul Hanifan | VL | Contract Details | RPT | 2018-12-14 | Approved |  |  | 100% | Selvaraj Mani | 100% | Tim Wilson | Yes |  | 2018-07-30 | 2018-09-06 | 2018-08-11 | 2018-09-10
Y | SRM1 | ID176 | Procure to Pay | SRM – Contract | BI-RPT-0093 | Paul Hanifan | VL | Contract Per Product Category | RPT |  | Approved |  |  | 100% | Selvaraj Mani | 100% | Tim Wilson | Yes |  | 2018-07-30 | 2018-09-06 | 2018-08-11 | 2018-09-10
Y | SRM1 | ID177 | Procure to Pay | SRM – Purchase Order (Procure to Pay) | BI-RPT-0094 | Paul Hanifan | VL | Purchase Order per Account Assignment | RPT |  | Approved |  |  | 100% | Selvaraj Mani | 100% | Tim Wilson | Yes |  | 2018-07-30 | 2018-09-06 | 2018-08-11 | 2018-09-05
Y | SRM1 | ID178 | Procure to Pay | SRM – Purchase Order (Procure to Pay) | BI-RPT-0095 | Paul Hanifan | VL | Purchase Order per Product Category | RPT |  | Approved |  |  | 100% | Selvaraj Mani | 100% | Tim Wilson | Yes |  | 2018-07-30 | 2018-09-07 | 2018-08-11 | 2018-09-06
Y | SRM1 | ID179 | Procure to Pay | SRM – Purchase Order (Procure to Pay) | BI-RPT-0096 | Paul Hanifan | VL | Purchase Order per Vendor & Catlog | RPT |  | Approved |  |  | 100% | Selvaraj Mani | 100% | Tim Wilson | Yes |  | 2018-07-30 | 2018-09-05 | 2018-08-11 | 2018-09-06
Y | SRM1 | ID180 | Procure to Pay | SRM – Purchase Order (Procure to Pay) | BI-RPT-0097 | Paul Hanifan | VL | Purchase order per Contracts | RPT |  | Approved |  |  | 100% | Selvaraj Mani | 100% | Tim Wilson | Yes |  | 2018-07-30 | 2018-09-07 | 2018-08-11 | 2018-09-06
Y | SRM1 | ID181 | Procure to Pay | SRM – Purchase Order (Procure to Pay) | BI-RPT-0098 | Paul Hanifan | VL | Purchase order per Shopping Carts | RPT |  | Approved |  |  | 100% | Selvaraj Mani | 100% | Tim Wilson | Yes |  | 2018-07-30 | 2018-09-07 | 2018-08-11 | 2018-09-07
Y | SRM1 | ID182 | Procure to Pay | SRM – Purchase Order (Procure to Pay) | BI-RPT-0099 | Paul Hanifan | VL | Purchase Order per Requester | RPT |  | Approved |  |  | 100% | Selvaraj Mani | 100% | Tim Wilson | Yes |  | 2018-11-12 | 2018-11-16 | 2018-08-11 | 2018-09-05
Y | SRM1 | ID183 | Procure to Pay | SRM – Bidding Engine | BI-RPT-0100 | Paul Hanifan | VL | Bidder's Bids in Detail | RPT |  | Approved |  |  | 100% | Selvaraj Mani | 100% | Tim Wilson | Yes |  | 2019-02-08 | 2019-02-14 | 2018-08-11 | 2018-09-07
Y | SRM1 | ID184 | Procure to Pay | SRM – Bidding Engine | BI-RPT-0101 | Paul Hanifan | VL | Bid Invitation Analysis By Product Category | RPT | 2018-12-19 | Approved |  |  | 100% | Selvaraj Mani | 100% | Tim Wilson | Yes |  | 2019-02-05 | 2019-02-14 | 2018-08-11 | 2018-09-07
Y | DBT1 | ID107 | Offer to Cash | Debt Management | ERP-RPT-0015 | Mary Loughran | L | List BP Details/Business Partner Master Data Report | RPT | 2018-06-12 | Approved | 100% | Kamaljit Singh | 100% | Selvaraj Mani | 100% | Tim Wilson | Yes |  | 2018-11-21 | 2018-11-28 | 2018-08-11 | 2018-09-04
Y | DBT1 | ID109 | Offer to Cash | Debt Management | ERP-RPT-0017 | Mary Loughran | M | Display class master data | RPT | 2018-09-21 | Approved | 100% | Kamaljit Singh | 100% | Selvaraj Mani | 100% | Tim Wilson | Yes |  | 2018-09-21 | 2018-09-27 | 2018-08-11 | 2018-10-06
Y | DBT1 | ID110 | Offer to Cash | Debt Management | ERP-RPT-0019 | Mary Loughran | M | Principal payment schedule | RPT | 2018-09-07 | Approved | 100% | Kamaljit Singh | 100% | Selvaraj Mani | 100% | Tim Wilson | Yes |  | 2018-10-09 | 2018-10-16 | 2018-10-24 | 2018-10-06
Y | DBT1 | ID111 | Offer to Cash | Debt Management | ERP-RPT-0021 | Mary Loughran | L | Annual report | RPT | 2018-09-07 | Approved | 100% | Kamaljit Singh | 100% | Selvaraj Mani | 100% | Tim Wilson | Yes |  | 2018-09-27 | 2018-10-09 | 2018-08-11 | 2018-09-21
Y | DBT1 | ID112 | Offer to Cash | Debt Management | ERP-RPT-0022 | Mary Loughran | VL | Debt Schedule Report | RPT | 2018-09-07 | Approved | 100% | Kamaljit Singh | 100% | Selvaraj Mani | 100% | Tim Wilson | Yes |  | 2018-12-06 | 2018-12-10 | 2018-08-11 | 2018-09-21
Y | DBT1 | ID115 | Offer to Cash | Debt Management | ERP-RPT-0029 | Mary Loughran | M | Outstanding Bonds | RPT | 2018-09-07 | Approved | 100% | Kamaljit Singh | 100% | Selvaraj Mani | 100% | Tim Wilson | Yes |  | 2018-12-14 | 2018-12-14 | 2018-08-11 | 2018-10-28
Y | INV2 | ID011 | Cash to Invest | Cash to Invest | ERP-RPT-0043 | Mary Loughran | VL | Trade list report | RPT | 2018-09-21 | Approved | 100% | Kamaljit Singh | 100% | Selvaraj Mani | 100% | Tim Wilson | Yes |  | 2018-11-12 | 2018-11-13 | 2018-11-16 | 2018-11-19
Y | PTR1 | ID118 | Plan to Report | FI-GL | BI-RPT-0001 | Tim Keohan | M | Statement of Net Position | RPT | 2018-12-19 | [9 empty] | 2018-12-27 | 2019-01-25
Y | HR1 | ID041 | Hire to Retire | Hire to Retire | BI-RPT-0078 | Rashed Siddiqui | L | BiWeekly Salaries(Leap year) | RPT |  | NA | NA |  | NA |  | NA |  | NA | n | 2018-07-30 | 2018-09-05 | [7 empty] | descoped CR_023
Y | PTR1 | ID119 | Plan to Report | FI-GL | BI-RPT-0002 | Tim Keohan | H | Statement of Revenues, Expenses and Changes in Net Position Report | RPT | 2018-12-07 | [9 empty] | 2018-12-25 | 2019-01-04
Y | PTR1 | ID120 | Plan to Report | FI-GL | BI-RPT-0003 | Tim Keohan | M | Statement of Cash Flow Report | RPT | 2018-12-05 | [9 empty] | 2018-12-17 | 2018-12-27
Y | HR1 | ID021 | Hire to Retire | Hire to Retire | BI-RPT-0006 | Rashed Siddiqui | L | Flexible labour distribution report | RPT | 2018-09-26 | waiting revision | [8 empty] | 2018-12-10 | 2018-12-20 | [7 empty] | On Hold, FS changes are required
Y | PTR3 | ID123 | Plan to Report | Public Sector management | BI-RPT-0010 | Tim Keohan | H | Budget Discrepencies | RPT | 2018-11-16 | Approved | [8 empty] | 2018-12-25 | 2019-01-09
N | SRM2 | ID209 | Procure to Pay | Procurement, Accounts Payable | BI-RPT-0037 | Paul Hanifan | L | Ability to query existing vendor master | RPT | 2018-09-20 | dependency | [8 empty] | 2019-01-09 | 2019-01-14
Y | INV1 | ID018 | Cash to Invest | Cash to Invest | BI-RPT-0051 | Mary Loughran | VL | GASB Investment Detail Report | RPT | 2018-09-14 | Approved | [8 empty] | 2018-12-18 | 2018-12-19
Y | PTR1 | ID124 | Plan to Report | FI-GL | BI-RPT-0057 | Tim Keohan | VL | Statement of Net Position - Supplementary Schedule | RPT | 2018-11-30 | [9 empty] | 2018-12-19 | 2018-12-21
Y | PTR1 | ID125 | Plan to Report | FI-GL | BI-RPT-0058 | Tim Keohan | VL | Statement of Revenues, Expenses and Changes in Net Position - Supplementary Schedule | RPT | 2018-12-12 | [9 empty] | 2019-01-07 | 2019-01-09
Y | DBT2 | ID173 | Offer to Cash | Loans | BI-RPT-0090 | Pablo Morrison | H | Cash flow and Loans | RPT |  | NA | NA |  | NA |  | NA |  | NA | n | 2018-07-30 | 2018-09-11 | [7 empty] | descoped CR_022
Y | PTR1 | ID126 | Plan to Report | FI-GL | BI-RPT-0059 | Tim Keohan | VL | Statement of Cash Flow - Supplementary Schedule | RPT | 2018-12-14 | [9 empty] | 2019-01-03 | 2019-01-07
Y | HR1 | ID023 | Hire to Retire | Hire to Retire | BI-RPT-0060 | Rashed Siddiqui | L | Deferred Compensation Report | RPT | 2018-09-28 | Approved | 100% | Kamaljit Singh | [6 empty] | 2018-12-28 | 2019-01-02
Y | HR1 | ID025 | Hire to Retire | Hire to Retire | BI-RPT-0062 | Rashed Siddiqui | VL | New York State Housing Finance Agency Union Dues Report | RPT | 2018-09-28 | Approved | 100% | Kamaljit Singh |  |  | 100% | Tim Wilson | Yes |  | 2018-12-12 | 2018-12-12 |  | 2018-11-30
Y | HR1 | ID026 | Hire to Retire | Hire to Retire | BI-RPT-0063 | Rashed Siddiqui | VL | New York State Housing Finance Agency SEFA Report | RPT | 2018-09-28 | Approved | 100% | Kamaljit Singh |  |  |  | Niveditha Chilka |  |  | 2018-12-12 | 2018-12-13
Y | HR1 | ID027 | Hire to Retire | Hire to Retire | BI-RPT-0064 | Rashed Siddiqui | VL | State of New York Mortgage Agency Life Insurance Report | RPT | 2018-09-28 | Approved | 100% | Kamaljit Singh |  |  | 100% | Niveditha Chilka | Yes |  | 2018-12-04 | 2018-12-04
Y | HR1 | ID028 | Hire to Retire | Hire to Retire | BI-RPT-0065 | Rashed Siddiqui | VL | NewYork State Housing Finance Agency AFLAC Life Insurance Report | RPT | 2018-09-28 | Approved | 100% | Kamaljit Singh |  |  |  | Niveditha Chilka |  |  | 2018-12-03 | 2018-12-04
Y | HR1 | ID029 | Hire to Retire | Hire to Retire | BI-RPT-0066 | Rashed Siddiqui | VL | NewYork State Housing Finance Agency Security Mutual Life Insurance Report | RPT | 2018-09-28 | Approved | 100% | Kamaljit Singh |  |  | 100% | Niveditha Chilka | Yes |  | 2019-01-07 | 2019-01-07
N | HR1 | ID030 | Hire to Retire | Hire to Retire | BI-RPT-0067 | Rashed Siddiqui | L | Wellness Earnings per Period | RPT | 2018-10-05 | Approved | 100% | Kamaljit Singh |  |  |  | Niveditha Chilka |  |  | 2019-01-03 | 2019-01-08
N | HR1 | ID031 | Hire to Retire | Hire to Retire | BI-RPT-0068 | Rashed Siddiqui | L | Etrac File Report | RPT | 2018-10-05 | Approved | 100% | Kamaljit Singh | [6 empty] | 2019-01-10 | 2019-01-14
N | HR1 | ID032 | Hire to Retire | Hire to Retire | BI-RPT-0069 | Rashed Siddiqui | L | Payroll Register Summary | RPT | 2018-10-05 | Approved | 100% | Kamaljit Singh | [6 empty] | 2019-01-16 | 2019-01-21
Y | HR1 | ID033 | Hire to Retire | Hire to Retire | BI-RPT-0070 | Rashed Siddiqui | VL | Monthly Pension Report | RPT | 2018-09-28 | Approved | 100% | Kamaljit Singh |  |  |  | Niveditha Chilka |  |  | 2018-12-10 | 2018-12-11
N | HR1 | ID034 | Hire to Retire | Hire to Retire | BI-RPT-0071 | Rashed Siddiqui | L | Disabilty Premium Calculation | RPT | 2018-10-10 | Approved | [8 empty] | 2019-01-22 | 2019-01-25 | [7 empty] | On Hold, FS changes are required
N | HR1 | ID035 | Hire to Retire | Hire to Retire | BI-RPT-0072 | Rashed Siddiqui | L | Overtime for Period(date to-from) | RPT | 2018-10-10 | Approved | 100% | Kamaljit Singh |  |  |  | Niveditha Chilka |  |  | 2019-01-29 | 2019-02-01
Y | HR1 | ID036 | Hire to Retire | Hire to Retire | BI-RPT-0073 | Rashed Siddiqui | L | Overtime for Period#2 | RPT | 2018-10-17 | Approved | 100% | Kamaljit Singh |  |  | 100% | Niveditha Chilka | Yes |  | 2018-12-06 | 2018-12-06
Y | HR1 | ID037 | Hire to Retire | Hire to Retire | BI-RPT-0074 | Rashed Siddiqui | VL | Annual Report Figures | RPT | 2018-10-03 | Approved | 90% | Kamaljit Singh |  |  |  | Niveditha Chilka |  |  | 2018-12-06 | 2018-12-07
Y | HR1 | ID038 | Hire to Retire | Hire to Retire | BI-RPT-0075 | Rashed Siddiqui | VL | Annual Pension Contributions | RPT | 2018-10-03 | Approved | 100% | Kamaljit Singh |  |  |  | Niveditha Chilka |  |  | 2018-12-03 | 2018-12-04
Y | HR1 | ID039 | Hire to Retire | Hire to Retire | BI-RPT-0076 | Rashed Siddiqui | VL | State Insurance Fund Report | RPT | 2018-10-03 | Approved | 90% | Kamaljit Singh | [6 empty] | 2018-12-12 | 2018-12-14
N | HR1 | ID040 | Hire to Retire | Hire to Retire | BI-RPT-0077 | Rashed Siddiqui | L | BiWeekly Payroll History | RPT | 2018-10-05 | Approved | 100% | Kamaljit Singh | [6 empty] | 2018-12-18 | 2019-01-01
Y | HR1 | ID042 | Hire to Retire | Hire to Retire | BI-RPT-0079 | Rashed Siddiqui | M | Salary Differences Payroll Register vs Personnel Salary History | RPT | 2018-10-05 | Approved | 100% | Kamaljit Singh |  |  | 100% | Tim Wilson | Yes |  | 2018-07-30 | 2018-09-10
|  |  | Hire to Retire | Hire to Retire | BI-RPT-0230 | Rashed Siddiqui | L | Deferred Compensation Age 50+ Report | RPT | 2018-11-12 | Approved | 100% | Kamaljit Singh |  |  | 100% | Tim Wilson | Yes |  | 2018-12-07 | 2018-12-10 | [7 empty] | CR_026
Y | TRV | ID022 | Hire to Retire | Travel Management | BI-RPT-0014 | Nick Zahiri | M | Travel Expense Reimbursment report. | RPT | 2018-09-26 | Approved |  |  | 100% | Selvaraj Mani | 100% | Tim Wilson | Yes |  | 2018-11-15 | 2018-11-23 |  | 2018-11-23
|  |  | Hire to Retire | Hire to Retire | BI-RPT-0231 | Rashed Siddiqui | L | FICA Projection Report | RPT | 2018-11-12 | [9 empty] | 2018-12-07 | 2018-12-07 | [7 empty] | CR_027; FS not available
|  |  | Hire to Retire | Hire to Retire | BI-RPT-0232 | Rashed Siddiqui | M | Payroll Allocations Report | RPT | 2018-11-12 | dependency | [8 empty] | 2019-01-28 | 2019-01-30 | [7 empty] | CR_028; On Hold
|  |  | Hire to Retire | Hire to Retire | BI-RPT-0233 | Rashed Siddiqui | VL | Staff Allocation - Salary Amount Report (Dollar Amount Report) | RPT | 2018-11-12 | dependency | [8 empty] | 2019-01-28 | 2019-01-30 | [7 empty] | CR_029; On Hold
|  |  | Hire to Retire | Hire to Retire | BI-RPT-0234 | Rashed Siddiqui | VL | Health Insurance Report | RPT | 2018-11-12 | Approved | 100% | Kamaljit Singh | [6 empty] | 2019-01-21 | 2019-01-23 | [7 empty] | CR_030
N | INV2 | ID346 | Cash to Invest | Cash to Invest | CTI-BI-RPT-0205 | Mary Loughran | M | Board Report | RPT | 2018-06-12 | [9 empty] | 2019-01-30 | 2019-02-14
N | INV2 | ID347 | Cash to Invest | Cash to Invest | CTI-BI-RPT-0206 | Mary Loughran | M | Market Value | RPT | 2018-09-21 | [9 empty] | 2019-01-30 | 2019-02-14
Y | PTR1 | ID121 | Plan to Report | FI-GL | ERP-RPT-0004 | Tim Keohan | H | Trial Balances Report | RPT | 2018-12-24 | [9 empty] | 2019-01-23 | 2019-02-11
Y | PTR3 | ID122 | Plan to Report | Public Sector management | ERP-RPT-0009 | Tim Keohan | H | Budget vs Actual | RPT | 2018-11-14 | Approved | [8 empty] | 2018-12-19 | 2019-01-07
Y | DBT2 | ID108 | Offer to Cash | Debt Management | ERP-RPT-0016 | Mary Loughran | H | Average Interest Rates for Remarketing Agents and Letter of Credit Providers or Enhancers Report | RPT | 2018-09-21 | Approved | [8 empty] | 2018-12-03 | 2018-12-21
Y | INV1 | ID012 | Cash to Invest | Cash to Invest | ERP-RPT-0044 | Mary Loughran | VL | Arbitrage Information | RPT | 2018-09-14 | Approved |  |  | 100% | Selvaraj Mani | 80% | Tim Wilson |  |  | 2019-02-12 | 2019-02-13
Y | INV1 | ID013 | Cash to Invest | Cash to Invest | ERP-RPT-0046 | Mary Loughran | VL | Summary of Investments Outstanding | RPT | 2018-09-14 | waiting revision | [8 empty] | 2018-12-14 | 2018-12-17
Y | INV1 | ID014 | Cash to Invest | Cash to Invest | ERP-RPT-0047 | Mary Loughran | VL | Investment Inventory Report | RPT | 2018-09-14 | Approved |  |  | 100% | Selvaraj Mani | 100% | Tim Wilson | Yes |  | 2018-12-28 | 2018-12-31 |  | 2018-11-30
Y | INV1 | ID015 | Cash to Invest | Cash to Invest | ERP-RPT-0048 | Mary Loughran | VL | Investment History Report | RPT | 2018-09-14 | Approved | [8 empty] | 2018-12-04 | 2018-12-05
Y | INV1 | ID016 | Cash to Invest | Cash to Invest | ERP-RPT-0049 | Mary Loughran | VL | Investment Interest and Maturity Report | RPT | 2018-09-14 | Approved |  |  | 100% | Selvaraj Mani | 50% | Tim Wilson |  |  | 2018-12-05 | 2018-12-06
Y | INV1 | ID019 | Cash to Invest | Cash to Invest | ERP-RPT-0053 | Mary Loughran | VL | OFI Cash Schedule | RPT | 2018-09-14 | Approved |  |  |  | Selvaraj Mani |  |  |  |  | 2018-12-28 | 2019-01-02
Y | INV1 | ID020 | Cash to Invest | Cash to Invest | ERP-RPT-0054 | Mary Loughran | VL | MIF Investments Reports | RPT | 2018-09-14 | waiting revision | [8 empty] | 2018-12-20 | 2018-12-24
N | HR2 | ID090 | Hire to Retire | Payroll Reports, From SOW | HTR-BI-RPT-0201 | Rashed Siddiqui | L | Pension | RPT | [9 empty] | n | 2018-12-07 | 2018-12-10 | [7 empty] | cr_042
N | HR2 | ID076 | Hire to Retire | Payroll Reports, From SOW | HTR-BI-RPT-0203 | Rashed Siddiqui | L | Payroll Reports, Ad hoc | RPT | [9 empty] | n | 2018-12-06 | 2018-12-07 | [7 empty] | cr_041
N | HR2 | ID043 | Hire to Retire | ECS Reports, From SOW | HTR-BI-RPT-0204 | Rashed Siddiqui | L | Employee Vendors - (Listing of Employee Vendor) - Optical Benefit requirement met as well) | RPT | 2018-10-10 | [9 empty] | 2018-12-11 | 2018-12-24
N | HR2 | ID096 | Hire to Retire | Payroll Reports, From SOW | HTR-BI-RPT-0207 | Rashed Siddiqui | L | Salary Comparison | RPT | [9 empty] | n | 2018-12-10 | 2018-12-10 | [7 empty] | cr_040
N | HR2 | ID105 | Hire to Retire | Hire to Retire | HTR-BI-RPT-0208 | Rashed Siddiqui | L | Staff Allocation for HFA | RPT | 2018-10-12 | waiting revision | [8 empty] | 2018-12-04 | 2018-12-07
N | HR2 | ID104 | Hire to Retire | Payroll Reports, From SOW | HTR-BI-RPT-0209 | Rashed Siddiqui | L | PARIS Report (New) | RPT | 2018-10-12 | Approved | 100% | Kamaljit Singh |  |  |  | Meiling Schumm |  |  | 2018-11-30 | 2018-12-05 |  | 2018-12-06
N | HR2 | ID103 | Hire to Retire | Payroll Reports, From SOW | HTR-BI-RPT-0210 | Rashed Siddiqui | L | FSA Payroll Deductions (New) | RPT | 2018-10-12 | Approved | 100% | Kamaljit Singh | [6 empty] | 2018-12-07 | 2018-12-11
Y | HR2 | ID097 | Hire to Retire | Payroll Reports, From SOW | HTR-BI-RPT-0211 | Rashed Siddiqui | M | Salary History | RPT | 2018-10-05 | Approved | 100% | Kamaljit Singh |  |  |  | Meiling Schumm | Y |  | 2018-12-06 | 2018-12-11 |  | 2018-12-06
N | HR2 | ID044 | Hire to Retire | HRIS, From SOW | HTR-BI-RPT-0212 | Rashed Siddiqui | M | Employee Lists ad hoc | RPT |  | NA | NA |  | NA |  | NA |  | NA | n | 2019-01-28 | 2019-01-29
N | HR2 | ID061 | Hire to Retire | HRIS, From SOW | HTR-BI-RPT-0214 | Rashed Siddiqui | L | Employee Lists, Salary Monthly | RPT |  | NA | NA |  | NA |  | NA |  | NA | n | 2018-12-17 | 2018-12-17
N | HR2 | ID060 | Hire to Retire | HRIS, From SOW | HTR-BI-RPT-0216 | Rashed Siddiqui | L | Employee Lists, Salary History | RPT |  | NA | NA |  | NA |  | NA |  | NA | n | 2019-01-07 | 2019-01-09
N | HR2 | ID047 | Hire to Retire | HRIS, From SOW | HTR-BI-RPT-0219 | Rashed Siddiqui | M | Compensated Absences (Accounting) | RPT |  | NA | NA |  | NA |  | NA |  | NA | n | 2019-01-07 | 2019-01-09
N | DBT2 | ID117 | Plan to Report | Tax Reports, From SOW | OTCD-BI-RPT-0213 | Tim Koehan | M | TICKLER REPORT | RPT | 2018-11-28 | [9 empty] | 2018-12-11 | 2018-12-14
N | DBT2 | ID116 | Plan to Report | Debt Management | OTCD-BI-RPT-0215 | Tim Koehan | M | SONYMA Schedule A | RPT | 2018-11-21 | [9 empty] | 2019-02-11 | 2019-02-14
N | SRM2 | ID191 | Procure to Pay | ECS Reports, From SOW | PTP-BI-RPT-0202 | Paul Hanifan | M | Payments - State Contract (Lisa) | RPT | 2018-09-20 | waiting revision | [8 empty] | 2018-12-05 | 2018-12-07
N | SRM2 | ID193 | Procure to Pay | ECS Reports, From SOW | PTP-BI-RPT-0222 | Paul Hanifan | M | Prompt Payment (Annual Report - Past 30 Days History -Inv Receipt Vs Payment Date | RPT | 2018-12-28 | [9 empty] | 2019-01-21 | 2019-01-23
Y | PTR3 | ID153 | Plan to Report | ECS Reports, From SOW | PTR-BI-RPT-0217 | Tim Keohan | VL | Budget Spreadsheet Replacements (Budget Vs Actual - Administrative) | RPT | 2018-12-14 | [8 empty] | n | 2018-12-20 | 2018-12-24 | [7 empty] | cr_032
Y | PTR3 | ID152 | Plan to Report | ECS Reports, From SOW | PTR-BI-RPT-0218 | Tim Keohan | VL | Budget Fiscal Year Records (Budget Vs Actual - Administrative) | RPT | 2018-12-19 | [8 empty] | n | 2018-12-25 | 2018-12-27 | [7 empty] | cr_035
N | PTR2 | ID164 | Plan to Report | GL Reports, From SOW | PTR-BI-RPT-0220 | Tim Keohan | H | Tax Ins Escrow Letters Form Letter to Management Companies Beg Balance Ending Balance | RPT | 2018-11-28 | [8 empty] | n | 2018-12-11 | 2019-01-07 | [7 empty] | cr_034
Y | PTR3 | ID150 | Plan to Report | ECS Reports, From SOW | PTR-BI-RPT-0221 | Tim Keohan | VL | Budget Allocation (Budget Vs Actual - Administrative) | RPT | 2018-12-12 | [8 empty] | n | 2018-12-26 | 2019-01-08 | [7 empty] | cr_033
Y | PTR3 | ID154 | Plan to Report | ECS Reports, From SOW | PTR-BI-RPT-0223 | Tim Keohan | VL | Budget Speadsheet Account Detail | RPT | 2018-12-28 | [9 empty] | 2019-01-14 | 2019-01-16
Y | PTR2 | ID159 | Plan to Report | ECS Reports, From SOW | PTR-BI-RPT-0224 | Tim Keohan | M | Wire Warrant | RPT | 2018-12-28 | [9 empty] | 2019-01-23 | 2019-02-07
Y | PTR2 | ID155 | Plan to Report | ECS Reports, From SOW | PTR-BI-RPT-0225 | Tim Keohan | L | Fringe Calculations (Cost Allocations- Agency Level) | RPT | 2018-12-28 | [9 empty] | 2019-01-29 | 2019-02-08
Y | PTR3 | ID151 | Plan to Report | ECS Reports, From SOW | PTR-BI-RPT-0226 | Tim Keohan | VL | Budget Discrepancies (Budget Vs Actual - Administrative) | RPT | 2018-12-14 | [9 empty] | 2019-01-15 | 2019-01-18
Y | PTR2 | ID149 | Plan to Report | ECS Reports, From SOW | PTR-BI-RPT-0227 | Tim Keohan | M | Payroll By Agency (HFA, Sonyma, AHC) | RPT | 2019-01-04 | [9 empty] | 2019-01-09 | 2019-02-12
Y | PTR2 | ID158 | Plan to Report | ECS Reports, From SOW | PTR-BI-RPT-0228 | Tim Keohan | M | Warrant (Dept Finance Payment Run - A/P) | RPT | 2019-01-04 | [9 empty] | 2019-01-09 | 2019-02-15
|  |  | Offer to Cash |  | BI-RPT-0237 | Mary Loughran | M | Annual Report for Bonds | RPT

## Reports
Business Process | RICEF Object | RICEF Object | Name of RICEFW Object | Complexity | RICEFW Type | Source System
Plan to Report | BI-ENH-0008 | BI-ENH-0008 | Custom BW Cubes to Support Organizational Structure Reporting | M | EHN | S4
Procure to Pay | BI-ENH-0016 | BI-ENH-0016 | Custom BW Cubes to Support Procurement Reporting | L | EHN | BW
Procure to Pay | BI-ENH-0017 | BI-ENH-0017 | Custom BW Extractor to Support Procurement Reporting | L | EHN | BW
Offer to Cash | BI-ENH-0025 | BI-ENH-0025 | SAP will not provide reporting of bonded debt information that will include all account assignment fields. | M | EHN | BW
Offer to Cash | BI-ENH-0026 | BI-ENH-0026 | Custom BW Cubes to Support Budget Development | L | EHN | BW
Procure to Pay | BI-ENH-0043 | BI-ENH-0043 | Custom BW Cubes to Support Vendor Reporting | L | EHN | BW
Procure to Pay | BI-ENH-0044 | BI-ENH-0044 | Custom BW Extractor to Support Vendor Reporting | L | EHN | BW
Procure to Pay | BI-ENH-0046 | BI-ENH-0046 | Custom BW Cubes to Support Debt Management Reporting | L | EHN | BW
Plan to Report | BI-RPT-0001 | BI-RPT-0001 | Statement of Net Position | M | RPT | S4
Plan to Report | BI-RPT-0002 | BI-RPT-0002 | Statement of Revenues, Expenses and Changes in Net Position - Supplementary Schedule | VL | RPT | S4
Plan to Report | BI-RPT-0003 | BI-RPT-0003 | Statement of Cash Flow Report | M | RPT | S4
Plan to Report | BI-RPT-0004 | BI-RPT-0004 | Trial Balances Report | H | RPT | S4
Hire to Retire | BI-RPT-0006 | BI-RPT-0006 | Flexible labour distribution report | L | RPT | S4
Plan to Report | ERP-RPT-0009 | BI-RPT-0009 | Budget vs Actual | H | RPT | S4
Plan to Report | BI-RPT-0010 | BI-RPT-0010 | Budget Discrepencies | H | RPT | S4
Hire to Retire | BI-RPT-0014 | BI-RPT-0014 | Travel Expense Reimbursment report. | M | RPT | S4
Offer to Cash | ERP-RPT-0015 | BI-RPT-0015 | List BP Details/Business Partner Master Data Report | L | RPT | BW
Offer to Cash | ERP-RPT-0016 | BI-RPT-0016 | Average Interest Rates for Remarketing Agents and Letter of Credit Providers or Enhancers Report | H | RPT | BW
Offer to Cash | ERP-RPT-0017 | BI-RPT-0017 | Display class master data | M | RPT | BW
Offer to Cash | ERP-RPT-0019 | BI-RPT-0019 | Principal payment schedule | M | RPT | BW
Offer to Cash | ERP-RPT-0021 | BI-RPT-0021 | Annual report | L | RPT | BW
Offer to Cash | ERP-RPT-0022 | BI-RPT-0022 | Debt Schedule Report | VL | RPT | BW
Offer to Cash | ERP-RPT-0026 | BI-RPT-0026 | Credit Enhancement | VL | RPT | BW
Offer to Cash | ERP-RPT-0029 | BI-RPT-0029 | Outstanding Bonds | M | RPT | BW
Procure to Pay | BI-RPT-0035 | BI-RPT-0035 | Flexible Organizational Structure Report | M | RPT | BW
Procure to Pay | BI-RPT-0036 | BI-RPT-0036 | Flexible Procurement | VL | RPT | BW
Procure to Pay | BI-RPT-0037 | BI-RPT-0037 | Ability to query existing vendor master | L | RPT | BW
Cash to Invest | ERP-RPT-0043 | BI-RPT-0043 | Trade list report | VL | RPT | BW
Cash to Invest | ERP-RPT-0044 | BI-RPT-0044 | Arbitrage Information | VL | RPT | BW
Cash to Invest | ERP-RPT-0046 | BI-RPT-0046 | Summary of Investments Outstanding | VL | RPT | BW
Cash to Invest | ERP-RPT-0047 | BI-RPT-0047 | Investment Inventory Report | VL | RPT | BW
Cash to Invest | ERP-RPT-0048 | BI-RPT-0048 | Investment History Report | VL | RPT | BW
Cash to Invest | ERP-RPT-0049 | BI-RPT-0049 | Investment Interest and Maturity Report | VL | RPT | BW
Cash to Invest | BI-RPT-0051 | BI-RPT-0051 | GASB Investment Detail Report | VL | RPT | BW
Cash to Invest | ERP-RPT-0053 | BI-RPT-0053 | OFI Cash Schedule | VL | RPT | BW
Cash to Invest | ERP-RPT-0054 | BI-RPT-0054 | MIF Investments Reports | VL | RPT | BW
Plan to Report | BI-RPT-0057 | BI-RPT-0057 | Statement of Net Position - Supplementary Schedule | VL | RPT | S4
Plan to Report | BI-RPT-0058 | BI-RPT-0058 | Statement of Revenues, Expenses and Changes in Net Position Report | H | RPT | S4
Plan to Report | BI-RPT-0059 | BI-RPT-0059 | Statement of Cash Flow - Supplementary Schedule | VL | RPT | S4
Hire to Retire | BI-RPT-0060 | BI-RPT-0060 | Deferred Compensation Report | L | RPT | S4
Hire to Retire | BI-RPT-0062 | BI-RPT-0062 | New York State Housing Finance Agency Union Dues Report | VL | RPT | S4
Hire to Retire | BI-RPT-0063 | BI-RPT-0063 | New York State Housing Finance Agency SEFA Report | VL | RPT | S4
Hire to Retire | BI-RPT-0064 | BI-RPT-0064 | State of New York Mortgage Agency Life Insurance Report | VL | RPT | S4
Hire to Retire | BI-RPT-0065 | BI-RPT-0065 | NewYork State Housing Finance Agency AFLAC Life Insurance Report | VL | RPT | S4
Hire to Retire | BI-RPT-0066 | BI-RPT-0066 | NewYork State Housing Finance Agency Security Mutual Life Insurance Report | VL | RPT | S4
Hire to Retire | BI-RPT-0067 | BI-RPT-0067 | Wellness Earnings per Period | L | RPT | S4
Hire to Retire | BI-RPT-0068 | BI-RPT-0068 | Etrac File Report | L | RPT | S4
Hire to Retire | BI-RPT-0069 | BI-RPT-0069 | Payroll Register Summary | L | RPT | S4
Hire to Retire | BI-RPT-0070 | BI-RPT-0070 | Monthly Pension Report | VL | RPT | S4
Hire to Retire | BI-RPT-0071 | BI-RPT-0071 | Disabilty Premium Calculation | L | RPT | S4
Hire to Retire | BI-RPT-0072 | BI-RPT-0072 | Overtime for Period(date to-from) | L | RPT | S4
Hire to Retire | BI-RPT-0073 | BI-RPT-0073 | Overtime for Period#2 | L | RPT | S4
Hire to Retire | BI-RPT-0074 | BI-RPT-0074 | Annual Report Figures | VL | RPT | S4
Hire to Retire | BI-RPT-0075 | BI-RPT-0075 | Annual Pension Contributions | VL | RPT | S4
Hire to Retire | BI-RPT-0076 | BI-RPT-0076 | State Insurance Fund Report | VL | RPT | S4
Hire to Retire | BI-RPT-0077 | BI-RPT-0077 | BiWeekly Payroll History | L | RPT | S4
Hire to Retire | BI-RPT-0078 | BI-RPT-0078 | BiWeekly Salaries(Leap year) | L | RPT | S4
Hire to Retire | BI-RPT-0079 | BI-RPT-0079 | Salary Differences Payroll Register vs Personnel Salary History | M | RPT | S4
Procure to Pay | BI-RPT-0083 | BI-RPT-0083 | Approval Times | VL | RPT | BW
Procure to Pay | BI-RPT-0084 | BI-RPT-0084 | Ordered Shopping Carts per Requester | VL | RPT | BW
Procure to Pay | BI-RPT-0085 | BI-RPT-0085 | Shopping Carts per Order | VL | RPT | BW
Procure to Pay | BI-RPT-0086 | BI-RPT-0086 | Shopping Carts per Account Assignment | VL | RPT | BW
Procure to Pay | BI-RPT-0087 | BI-RPT-0087 | Shopping Carts per Product Category | VL | RPT | BW
Procure to Pay | BI-RPT-0088 | BI-RPT-0088 | Shopping Carts per Vendor & Catalog | VL | RPT | BW
Procure to Pay | BI-RPT-0089 | BI-RPT-0089 | Status of Shopping Carts | VL | RPT | BW
Procure to Pay | BI-RPT-0090 | BI-RPT-0090 | Contract Cockpit Spend | H | RPT | BW
Procure to Pay | BI-RPT-0091 | BI-RPT-0091 | Contract Alerts | VL | RPT | BW
Procure to Pay | BI-RPT-0092 | BI-RPT-0092 | Contract Details | VL | RPT | BW
Procure to Pay | BI-RPT-0093 | BI-RPT-0093 | Contract Per Product Category | VL | RPT | BW
Procure to Pay | BI-RPT-0094 | BI-RPT-0094 | Purchase Order per Account Assignment | VL | RPT | BW
Procure to Pay | BI-RPT-0095 | BI-RPT-0095 | Purchase Order per Product Category | VL | RPT | BW
Procure to Pay | BI-RPT-0096 | BI-RPT-0096 | Purchase Order per Vendor & Catlog | VL | RPT | BW
Procure to Pay | BI-RPT-0097 | BI-RPT-0097 | Purchase order per Contracts | VL | RPT | BW
Procure to Pay | BI-RPT-0098 | BI-RPT-0098 | Purchase order per Shopping Carts | VL | RPT | BW
Procure to Pay | BI-RPT-0099 | BI-RPT-0099 | Purchase Order per Requester | VL | RPT | BW
Procure to Pay | BI-RPT-0100 | BI-RPT-0100 | Bidder's Bids in Detail | VL | RPT | BW
Procure to Pay | BI-RPT-0101 | BI-RPT-0101 | Bid Invitation Analysis By Product Category | VL | RPT | BW
Hire to Retire | HTR-BI-RPT-0201 | BI-RPT-0201 | Pension | L | RPT | S4
Procure to Pay | PTP-BI-RPT-0202 | BI-RPT-0202 | Payments - State Contract (Lisa) | M | RPT | BW
Hire to Retire | HTR-BI-RPT-0203 | BI-RPT-0203 | Payroll Reports, Ad hoc | L | RPT | S4
Plan to Report | HTR-BI-RPT-0204 | BI-RPT-0204 | Employee Vendors - (Listing of Employee Vendor) - Optical Benefit requirement met as well) | L | RPT | S4
Cash to Invest | CTI-BI-RPT-0205 | BI-RPT-0205 | Board Report | M | RPT | BW
Cash to Invest | CTI-BI-RPT-0206 | BI-RPT-0206 | Market Value | M | RPT | BW
Hire to Retire | HTR-BI-RPT-0207 | BI-RPT-0207 | Salary Comparison | L | RPT | S4
Hire to Retire | HTR-BI-RPT-0208 | BI-RPT-0208 | Staff Allocation for HFA | L | RPT | S4
Hire to Retire | HTR-BI-RPT-0209 | BI-RPT-0209 | PARIS Report (New) | L | RPT | S4
Hire to Retire | HTR-BI-RPT-0210 | BI-RPT-0210 | FSA Payroll Deductions (New) | L | RPT | S4
Hire to Retire | HTR-BI-RPT-0211 | BI-RPT-0211 | Salary History | M | RPT | S4
Hire to Retire | HTR-BI-RPT-0212 | BI-RPT-0212 | Employee Lists ad hoc | M | RPT | S4
Plan to Report | OTCD-BI-RPT-0213 | BI-RPT-0213 | TICKLER REPORT | M | RPT | S4
Hire to Retire | HTR-BI-RPT-0214 | BI-RPT-0214 | Employee Lists, Salary Monthly | L | RPT | S4
Plan to Report | OTCD-BI-RPT-0215 | BI-RPT-0215 | SONYMA Schedule A | M | RPT | S4
Hire to Retire | HTR-BI-RPT-0216 | BI-RPT-0216 | Employee Lists, Salary History | L | RPT | S4
Plan to Report | PTR-BI-RPT-0217 | BI-RPT-0217 | Budget Spreadsheet Replacements (Budget Vs Actual - Administrative) | VL | RPT | S4
Plan to Report | PTR-BI-RPT-0218 | BI-RPT-0218 | Budget Fiscal Year Records (Budget Vs Actual - Administrative) | VL | RPT | S4
Hire to Retire | HTR-BI-RPT-0219 | BI-RPT-0219 | Compensated Absences (Accounting) | M | RPT | S4
Plan to Report | PTR-BI-RPT-0220 | BI-RPT-0220 | Tax Ins Escrow Letters Form Letter to Management Companies Beg Balance Ending Balance | H | RPT | S4
Plan to Report | PTR-BI-RPT-0221 | BI-RPT-0221 | Budget Allocation (Budget Vs Actual - Administrative) | VL | RPT | S4
Plan to Report | PTP-BI-RPT-0222 | BI-RPT-0222 | Prompt Payment (Annual Report - Past 30 Days History -Inv Receipt Vs Payment Date | M | RPT | BW
Plan to Report | PTR-BI-RPT-0223 | BI-RPT-0223 | Budget Speadsheet Account Detail | VL | RPT | S4
Plan to Report | PTR-BI-RPT-0224 | BI-RPT-0224 | Wire Warrant | M | RPT | S4
Plan to Report | PTR-BI-RPT-0225 | BI-RPT-0225 | Fringe Calculations (Cost Allocations- Agency Level) | L | RPT | S4
Plan to Report | PTR-BI-RPT-0226 | BI-RPT-0226 | Budget Discrepancies (Budget Vs Actual - Administrative) | VL | RPT | S4
Plan to Report | PTR-BI-RPT-0227 | BI-RPT-0227 | Payroll By Agency (HFA, Sonyma, AHC) | M | RPT | S4
Plan to Report | PTR-BI-RPT-0228 | BI-RPT-0228 | Warrant (Dept Finance Payment Run - A/P) | M | RPT | S4
Hire to Retire | BI-RPT-0230 | BI-RPT-0230 | Deferred Compensation Age 50+ Report | L | RPT | S4
Hire to Retire | BI-RPT-0231 | BI-RPT-0231 | FICA Projection Report | L | RPT | S4
Hire to Retire | BI-RPT-0232 | BI-RPT-0232 | Payroll Allocations Report | M | RPT | S4
Hire to Retire | BI-RPT-0233 | BI-RPT-0233 | Staff Allocation - Salary Amount Report (Dollar Amount Report) | VL | RPT | S4
Hire to Retire | BI-RPT-0234 | BI-RPT-0234 | Health Insurance Report | VL | RPT | S4
Offer to Cash | BI-RPT-0237 | BI-RPT-0237 | Annual Report for Bonds | M | RPT | BW
Hire to Retire | HTR-BI-RPT-0244 | BI-RPT-0244 | Parking Deduction Report | L | RPT | S4
Offer to Cash |  |  | Cash flow and Loans | H | RPT | BW